## Tidal Valves
Outfall | Diameter (in) | Estimated New Tidal Valve Cost1 | Estimated Installation Cost2 | Estimated Total Cost
Quebec | 14 | 4000 | 2000 | 6000
Julian | 12 | 2400 | 1200 | 3600
Radcliffe | 24 | 10500 | 5300 | 15800
Brighton | 24 | 10500 | 5300 | 15800
Warwick | 36 | 18300 | 9200 | 27500
Kent | 24 | 10500 | 5300 | 15800
Sagamore | 24 | 10500 | 5300 | 15800
Island Parkway | 15 | 5000 | 2500 | 7500
Suffolk | 14 | 4000 | 2000 | 6000
Suffolk Beach | 14 | 4000 | 2000 | 6000
Roosevelt | 12 | 2400 | 1200 | 3600
Beach Way | 36 | 18300 | 9200 | 27500
Outfall Norfolk/ Marina | 14 | 4000 | 2000 | 6000
Rizkin | 16 | 6200 | 3100 | 9300
Redfield | 16 | 6200 | 3100 | 9300
Norfolk | 8 | 1200 | 600 | 1800
Waterford N | 36 | 18300 | 9200 | 27500
Long Beach Blvd | 30 | 11500 | 5800 | 17300
Right of Way | 8 | 1200 | 600 | 1800
Subtotal |  | - |  | 224000
Engineering Design |  | - |  | 18000
Environmental Review |  | - |  | 10000
Permitting |  | - |  | 10000
Bid Management & Construction Oversight |  | - |  | 25000
Estimated Total |  | - |  | 287000
Notes:
- 1 Tidal valve replacement cost estimates based on preliminary pricing from Red Valve ® TideFlex®
Technologies for TF-Series duckbill tidal valves.
- 2 Installation costs are assumed to be approximately 50% of the material costs. (Based on previous installation costs)
- Annual O & M costs for the tidal valves are estimated at $10,000 per year.
- O&M shall include semi-annual inspections of tide valves to evaluate condition. The Village shall perform regular repairs/cleaning as needed to maintain effective performance.
Actual costs will be determined based on Phase II design specifications and contractor bidding.

## Piping 18
Item | Unit Cost |  | Quantity |  | Estimated Cost
Surveying3 | 4000 | /day | 10 | days | 40000
18 inch Pipe1 | 90 | /ft | 1000 | ft | 90000
Trenching1 | 20 | /ft | 1000 | ft | 20000
Pipe Bedding1 | 1.5 | /cf | 29000 | cf | 43500
Backfill Trench1 | 10 | /ft | 1000 | ft | 10000
Curb Installation1 | 60 | /ft | 2000 | ft | 120000
Sidewalk Replacement1 | 60 | /ft | 1000 | ft | 60000
Catch Basin Installation1 | 7500 | /unit | 10 | units | 75000
Asphalt Restoration of Road1 | 180 | /ft | 1000 | ft | 180000
Waste Hauling2 | 25 | /cy | 1200 | cy | 30000
Disposal2 | 75 | /cy | 1200 | cy | 90000
Shoring Boxes3 | 3000 | /day | 35 | days | 105000
Dewatering2 | 500 | /day | 35 | days | 17500
Traffic Management2 | 2200 | /day | 35 | days | 77000
Utility Relocation2 | 60000 | each | 1 | unit | 60000
Subtotal/1,000 ft | - |  |  |  | 1018000
Engineering Design | - |  |  |  | 112000
Environmental Review | - |  |  |  | 3000
Permitting | - |  |  |  | 3000
Bid Management & Construction Oversight | - |  |  |  | 60000
Subtotal/1,000 ft | - |  |  |  | 1196000
Estimated Total | Assumes | 5500 | ft of piping installed |  | 6578000
Notes:
- 1 Cost estimates based on R.S. Means Building Construction Cost Data.
- 2 Cost estimates based on previously supplied contractor costs.
- 3 Cost estimates based on quoted costs.
- Annual O & M costs for the roadways and drainage infrastructure throughout the Village are estimated at approximately $75,000 per year.
- O&M shall include semi-annual inspections of the drainage system infrastructure to evaluate its condition and the need for cleaning and repairs. The Village shall perform regular catch basin cleaning and drainage pipe jetting as needed to prevent the accumulation of sediment and debris.
Actual costs will be determined based on Phase II design specifications and contractor bid pricing.

## Piping 20
Item | Unit Cost |  | Quantity |  | Estimated Cost
Surveying3 | 4000 | /day | 10 | days | 40000
20 inch Pipe1 | 100 | /ft | 1000 | ft | 100000
Trenching1 | 20 | /ft | 1000 | ft | 20000
Pipe Bedding1 | 1.5 | /cf | 29000 | cf | 43500
Backfill Trench1 | 10 | /ft | 1000 | ft | 10000
Curb Installation1 | 60 | /ft | 2000 | ft | 120000
Sidewalk Replacement1 | 60 | /ft | 1000 | ft | 60000
Catch Basin Installation1 | 7500 | /unit | 10 | units | 75000
Asphalt Restoration of Road1 | 180 | /ft | 1000 | ft | 180000
Waste Hauling2 | 25 | /cy | 1200 | cy | 30000
Disposal2 | 75 | /cy | 1200 | cy | 90000
Shoring Boxes3 | 3000 | /day | 35 | days | 105000
Dewatering2 | 500 | /day | 35 | days | 17500
Traffic Management2 | 2200 | /day | 35 | days | 77000
Utility Relocation2 | 60000 | each | 1 | unit | 60000
Subtotal/1,000 ft | - |  |  |  | 1028000
Engineering Design | - |  |  |  | 114000
Environmental Review | - |  |  |  | 3000
Permitting | - |  |  |  | 3000
Bid Management & Construction Oversight | - |  |  |  | 60000
Subtotal/1,000 ft | - |  |  |  | 1208000
Estimated Total | Assumes | 1200 | ft of piping installed |  | 1450000
Notes:
- 1 Cost estimates based on R.S. Means Building Construction Cost Data.
- 2 Cost estimates based on previously supplied contractor costs.
- 3 Cost estimates based on quoted costs.
- Annual O & M costs for the roadways and drainage infrastructure throughout the Village are estimated at approximately $75,000 per year.
- O&M shall include semi-annual inspections of the drainage system infrastructure to evaluate its condition and the need for cleaning and repairs. The Village shall perform regular catch basin cleaning and drainage pipe jetting as needed to prevent the accumulation of sediment and debris.
Actual costs will be determined based on Phase II design specifications and contractor bid pricing.

## Piping 24
Item | Unit Cost |  | Quantity |  | Estimated Cost
Surveying3 | 4000 | /day | 10 | days | 40000
24 inch Pipe1 | 125 | /ft | 1000 | ft | 125000
Trenching1 | 20 | /ft | 1000 | ft | 20000
Pipe Bedding1 | 1.5 | /cf | 29000 | cf | 43500
Backfill Trench1 | 10 | /ft | 1000 | ft | 10000
Curb Installation1 | 60 | /ft | 2000 | ft | 120000
Sidewalk Replacement1 | 60 | /ft | 1000 | ft | 60000
Catch Basin Installation1 | 7500 | /unit | 10 | units | 75000
Asphalt Restoration of Road1 | 180 | /ft | 1000 | ft | 180000
Waste Hauling2 | 25 | /cy | 1300 | cy | 32500
Disposal2 | 75 | /cy | 1300 | cy | 97500
Shoring Boxes3 | 3000 | /day | 35 | days | 105000
Dewatering2 | 500 | /day | 35 | days | 17500
Traffic Management2 | 2200 | /day | 35 | days | 77000
Utility Relocation2 | 60000 | each | 1 | unit | 60000
Subtotal/1,000 ft | - |  |  |  | 1063000
Engineering Design | - |  |  |  | 117000
Environmental Review | - |  |  |  | 3000
Permitting | - |  |  |  | 3000
Bid Management & Construction Oversight | - |  |  |  | 60000
Subtotal /1,000 ft | - |  |  |  | 1246000
Estimated Total | Assumes | 7800 | ft of piping installed |  | 9719000
Notes:
- 1 Cost estimates based on R.S. Means Building Construction Cost Data.
- 2 Cost estimates based on previously supplied contractor costs.
- 3 Cost estimates based on quoted costs.
- Annual O & M costs for the roadways and drainage infrastructure throughout the Village are estimated at approximately $75,000 per year.
- O&M shall include semi-annual inspections of the drainage system infrastructure to evaluate its condition and the need for cleaning and repairs. The Village shall perform regular catch basin cleaning and drainage pipe jetting as needed to prevent the accumulation of sediment and debris.
Actual costs will be determined based on Phase II design specifications and contractor bid pricing.

## Piping 36
Item | Unit Cost |  | Quantity |  | Estimated Cost
Surveying3 | 4000 | /day | 10 | days | 40000
36 inch Pipe1 | 225 | /ft | 1000 | ft | 225000
Trenching1 | 25 | /ft | 1000 | ft | 25000
Pipe Bedding1 | 1.5 | /cf | 32000 | cf | 48000
Backfill Trench1 | 10 | /ft | 1000 | ft | 10000
Curb Installation1 | 60 | /ft | 2000 | ft | 120000
Sidewalk Replacement1 | 60 | /ft | 1000 | ft | 60000
Catch Basin Installation1 | 7500 | /unit | 10 | units | 75000
Asphalt Restoration of Road1 | 180 | /ft | 1000 | ft | 180000
Waste Hauling2 | 25 | /cy | 2000 | cy | 50000
Disposal2 | 75 | /cy | 2000 | cy | 150000
Shoring Boxes3 | 3000 | /day | 35 | days | 105000
Dewatering2 | 500 | /day | 35 | days | 17500
Traffic Management2 | 2200 | /day | 35 | days | 77000
Utility Relocation2 | 60000 | each | 1 | unit | 60000
Subtotal/1,000 ft | - |  |  |  | 1242500
Engineering Design | - |  |  |  | 137000
Environmental Review | - |  |  |  | 3000
Permitting | - |  |  |  | 3000
Bid Management & Construction Oversight | - |  |  |  | 60000
Subtotal/1,000 ft | - |  |  |  | 1445500
Estimated Total | Assumes | 10500 | ft of piping installed |  | 15178000
Notes:
- 1 Cost estimates based on R.S. Means Building Construction Cost Data.
- 2 Cost estimates based on previously supplied contractor costs.
- 3 Cost estimates based on quoted costs.
- Annual O & M costs for the roadways and drainage infrastructure throughout the Village are estimated at approximately $75,000 per year.
- O&M shall include semi-annual inspections of the drainage system infrastructure to evaluate its condition and the need for cleaning and repairs. The Village shall perform regular catch basin cleaning and drainage pipe jetting as needed to prevent the accumulation of sediment and debris.
Actual costs will be determined based on Phase II design specifications and contractor bid pricing.

## Bulkheads
Location | Unit Cost per Foot | Estimated Feet of Bulkhead | Estimated Cost1
Norfolk Road North | 3800 | 40 | 152000
Redfield Road | 3800 | 40 | 152000
Rizkin Place | 3800 | 45 | 171000
Sherborne Place | 3800 | 150 | 570000
Washington Place | 3800 | 135 | 513000
Julian Place (headwall) | 3800 | 10 | 38000
Waterford Road North (headwall) | 3800 | 5 | 19000
Right of Way (headwall) | 3800 | 5 | 19000
Subtotal |  | - | 1634000
Engineering Design |  | - | 131000
Environmental Review |  | - | 15000
Permitting |  | - | 40000
Bid Management & Construction Oversight |  | - | 60000
Estimated Total |  | - | 1880000
1. Redfield was previously measured for bid purposes as 36ft |  |  | Average cost = $93,469. Compounded at 3% annually =
2. Norfolk was previously measured for bid purposes as 34ft. |  |  | Average cost = $100,207. Compounded at 3% annually =
3. Rizkin was previously measured as 45ft. |  |  | Average cost = $112,322. Compounded at 3% annually =
Average price per foot for three bulkheads:
#REF! |  |  | 115
Notes:
- 1Assumes bulkhead replacement cost is approximately $3,800 per linear foot. Cost based on previous contractor prices for bulkhead installation
- Annual O & M costs for the bulkheads are estimated at $10,000 per year.
- O&M shall include semi-annual inspections of bulkheads to evaluate condition. The Village shall perform regular repairs as needed to maintain the bulkheads.
Actual costs will be determined based on Phase II design specifications and contractor bid pricing.

## Pervious Paving Masone Beach
Item | Unit Cost |  | Quantity |  | Estimated Cost
Surveying2 | 4000 | /lot | 1 | lot | 4000
GPR Markout2 | 3500 | /day | 1 | day | 3500
Excavation2 | 1.5 | /cf | 11000 | cf | 16500
Hauling2 | 25 | /cy | 420 | cy | 10500
Disposal3 | 75 | /cy | 420 | cy | 31500
Sand Bedding2 | 250 | /cy | 210 | cy | 52500
Geotextile3 | 0.5 | /sf | 11000 | sf | 5500
Installation2 | 1.5 | /sf | 11000 | sf | 16500
Pervious Paving 2 | 7 | /sf | 11000 | sf | 77000
Subtotal | - |  |  |  | 218000
Engineering Design | - |  |  |  | 18000
Environmental Review | - |  |  |  | 5000
Permitting | - |  |  |  | 5000
Bid Management & Construction Oversight | - |  |  |  | 27000
Estimated Total | - |  |  |  | 273000
Notes:
- 1 Cost estimates based on R.S. Means Building Construction Cost Data.
- 2 Cost estimates based on previously supplied contractor costs.
- 3 Cost estimates based on quoted costs.
- Annual O & M costs to maintain pervious parking areas are estimated at $5,000 per year per parking lot.
- O&M shall include regular weeding during the summer months and semi-annual cleaning with a high pressure hose to maintain flow through the pavers.
Actual costs will be determined based on Phase II design specifications and contractor bid pricing.
Note on F6: Darren J. Ikin: pg 555 1-4' deep 1/2CY excavator
Note on F9: Darren J. Ikin: pg79 Sand screened and washed at pit. 10 mile haul

## Pervious Paving Bank of Amer
Item | Unit Cost |  | Quantity |  | Estimated Cost
Surveying2 | 4000 | /lot | 1 | lot | 4000
GPR Markout2 | 3500 | /day | 1 | day | 3500
Excavation2 | 1.5 | /cf | 11500 | cf | 17250
Hauling2 | 25 | /cy | 450 | cy | 11250
Disposal3 | 75 | /cy | 450 | cy | 33750
Sand Bedding2 | 250 | /cy | 225 | cy | 56250
Geotextile3 | 0.5 | /sf | 11500 | sf | 5750
Installation2,4 | 2 | /sf | 11500 | sf | 23000
Pervious Paving 2 | 7 | /sf | 11500 | sf | 80500
Subtotal | - |  |  |  | 236000
Engineering Design | - |  |  |  | 19000
Environmental Review | - |  |  |  | 5000
Permitting | - |  |  |  | 5000
Bid Management & Construction Oversight | - |  |  |  | 32000
Estimated Total | - |  |  |  | 297000
Notes:
- 1 Cost estimates based on R.S. Means Building Construction Cost Data.
- 2 Cost estimates based on previously supplied contractor costs.
- 3 Cost estimates based on quoted costs.
- 4 Estimated installation costs account for the curbs/edges around the former Bank of America parking lot.
- Annual O & M costs to maintain pervious parking areas are estimated at $5,000 per year per parking lot.
- O&M shall include regular weeding during the summer months and semi-annual cleaning with a high pressure hose to maintain flow through the pavers.
Actual costs will be determined based on Phase II design specifications and contractor bid pricing.

## Street Park Infiltration Beds
Item | Unit Cost |  | Quantity |  | Estimated Cost
Survey2 | 4000 | /lot | 1 | lot | 4000
Plant selections3, 4 | 15 | /plant | 300 | plants | 4500
Base gravel, media, garden bed stones2 | 6000 | each | 1 | unit | 6000
Excavation2 | 1.5 | /cf | 1800 | cf | 2700
Hauling2 | 25 | /cy | 70 | cy | 1800
Disposal3 | 75 | /cy | 70 | cy | 5300
Geotextile3 | 0.5 | /sf | 1800 | sf | 900
Installation2 | 1500 | /day | 5 | days | 7500
Curb Inlet Reshaping/ Restoration2 | 110 | /ft | 20 | ft | 2200
Traffic Management2 | 1000 | /day | 5 | days | 5000
Subtotal per site | - |  |  |  | 40000
7 sites across Village | 40000 | /site | 7 | sites | 280000
GPR Markout2 | 3500 | /day | 2 | days | 7000
Subtotal for 7 sites | - |  |  |  | 287000
Engineering Design | - |  |  |  | 49000
Environmental Review | - |  |  |  | 8000
Permitting | - |  |  |  | 8000
Bid Management & Construction Oversight | - |  |  |  | 45000
Estimated Total | - |  |  |  | 397000
Notes:
- 1 Cost estimates based on R.S. Means Building Construction Cost Data.
- 2 Cost estimates based on previously supplied contractor costs.
- 3 Cost estimates based on quoted costs.
- 4 Estimate based on 9 plants per square yard.
- Annual O & M costs for the infiltration beds are estimated at $3,000 per year per site, totalling approximately $21,000 per year.
- O&M shall include regular inspections and removal of trash/debris, as well as weeding during the summer months.
Actual costs will be determined based on Phase II design specifications and contractor bid pricing.

## Bioretention Street Trees
Item | Unit Cost |  | Quantity |  | Estimated Cost
9'x17' Stormtree®3 System (includes structure, grate/ inlet, engineered media) | 14000 | /system | 1 | system | 14000
Base gravel, Tree2 | 1200 | each | 1 | unit | 1200
Excavation2 | 1.5 | /cf | 620 | cf | 1000
Hauling2 | 25 | /cy | 25 | cy | 700
Disposal3 | 75 | /cy | 25 | cy | 1900
Geotextile3 | 0.5 | /sf | 300 | sf | 200
Installation2 | 1500 | /site | 1 | site | 1500
Traffic Management2 | 1000 | /day | 1 | day | 1000
Subtotal per tree | - |  |  |  | 22000
50 tree installations across Village | 22000 | /site | 50 | sites | 1100000
GPR Markout2 | 3500 | /day | 3 | days | 10500
Subtotal for 50 trees | - |  |  |  | 1111000
Engineering Design | - |  |  |  | 50000
Environmental Review | - |  |  |  | 8000
Permitting | - |  |  |  | 8000
Bid Management & Construction Oversight | - |  |  |  | 30000
Estimated Total | - |  |  |  | 1207000
Notes:
- 1 Cost estimates based on R.S. Means Building Construction Cost Data.
- 2 Cost estimates based on previously supplied contractor costs.
- 3 Cost estimates based on quoted costs.
- Annual O & M costs for the street trees are estimated at approximately $20,000 per year.
- O&M shall include regular inspections and removal of trash/debris, as well as weeding during the summer months.
Actual costs will be determined based on Phase II design specifications and contractor bid pricing.

## Swale
Item | Unit Cost |  | Quantity |  | Estimated Cost
Surveying2 | 4000 | /day | 1 | day | 4000
Excavation2 | 1.5 | /cf | 900 | cf | 1400
Hauling2 | 25 | /cy | 40 | cy | 1000
Disposal3 | 75 | /cy | 40 | cy | 3000
Media - Sand2 | 250 | /cy | 15 | cy | 4000
Media - 3/8" gravel2 | 200 | /cy | 15 | cy | 3000
Plants/decorative rocks2 | 100 | /sy | 70 | sy | 7000
Overflow Piping2 | 2000 | /section | 1 | section | 2000
Geotextile3 | 0.5 | /sf | 1200 | sf | 600
Installation2 | 15000 | /swale | 1 | swale | 15000
Restoration of Surfaces2 | 12000 | /swale | 1 | swale | 12000
Traffic Management2 | 1000 | /day | 5 | days | 5000
Subtotal per Swale | - |  |  |  | 58000
5 swales across Village | 58000 | /swale | 5 | swales | 290000
GPR Markout2 | 3500 | /day | 2 | days | 7000
Subtotal for 5 Swale Sites | - |  |  |  | 297000
Engineering Design | - |  |  |  | 35000
Environmental Review | - |  |  |  | 8000
Permitting | - |  |  |  | 8000
Bid Management & Construction Oversight | - |  |  |  | 40000
Estimated Total | - |  |  |  | 388000
Notes:
- 1 Cost estimates based on R.S. Means Building Construction Cost Data.
- 2 Cost estimates based on previously supplied contractor costs.
- 3 Cost estimates based on quoted costs.
- 4 Assumes each swale is 200 ft long x 3 ft wide
- Annual O & M costs for the bioswales are estimated at $3,000 per year per site, totalling approximately $15,000 per year.
- O&M shall include regular inspections and removal of trash/debris, as well as weeding during the summer months.
Actual costs will be determined based on Phase II design specifications and contractor bid pricing.

## Beach Replenishment
Item | Unit Cost |  | Quantity |  | Estimated Cost
Surveying2 | 4000 | /day | 3 | days | 12000
Media - Sand3 | 50 | /cy | 3000 | cy | 150000
Sand Delivery and Spreading3 | 30 | /cy | 3000 | cy | 90000
Plants/includes planting3 | 15 | /plant | 500 | plants | 7500
Jute Mat3 | 200 | /roll | 2 | rolls | 400
Rip Rap/Stabilization Materials2 | 300 | /ft | 400 | feet | 120000
Installation/Site Work2 | 15000 | /site | 2 | sites | 30000
Subtotal | - |  |  |  | 410000
Engineering Design | - |  |  |  | 33000
Environmental Review | - |  |  |  | 15000
Permitting | - |  |  |  | 25000
Bid Management & Construction Oversight | - |  |  |  | 25000
Estimated Total | - |  |  |  | 508000
Notes:
- 1 Cost estimates based on R.S. Means Building Construction Cost Data.
- 2 Cost estimates based on previously supplied contractor costs.
- 3 Cost estimates based on quoted costs.
- Annual O & M costs for the beach stabilization measures are estimated at $10,000 per year.
- O&M shall include regular removal of trash/debris and inspections for signs of beach erosion. Sand will be imported and stabilization measures will be repaired as needed. Plantings will be weeded during the summer months.
Actual costs will be determined based on Phase II design specifications and contractor bid pricing.

## Knee Wall
Item | Unit Cost |  | Quantity |  | Estimated Cost
Surveying2 | 4000 | /day | 3 | days | 12000
Excavation2 | 500 | /property | 37 | properties | 18500
Installation2 | 3000 | /property | 37 | properties | 111000
Hauling2 | 25 | /cubic yard | 200 | cubic yard | 5000
Waste / Sediment Disposal3 | 75 | /cubic yard | 200 | cubic yard | 15000
Fence Restoration2 | 1000 | /property | 37 | properties | 37000
Pool Restoration2 | 5000 | /property | 5 | properties | 25000
Tree Relocation2 | 4200 | /property | 15 | properties | 63000
Shed Relocation2 | 3000 | /property | 12 | properties | 36000
Deck Restoration2 | 1500 | /property | 1 | properties | 1500
Concrete Restoration2 | 3500 | /property | 5 | properties | 17500
Legal Fees / Agreements2 | 15000 | each | 1 | unit | 15000
GPR Markout2 | 3500 | /day | 4 | days | 14000
Subtotal4,5 | - |  |  |  | 371000
Engineering Design | - |  |  |  | 30000
Consultation with Residents/LIRR | - |  |  |  | 15000
Environmental Review | - |  |  |  | 5000
Permitting | - |  |  |  | 5000
Bid Management & Construction Oversight | - |  |  |  | 25000
Estimated Total | - |  |  |  | 451000
Notes:
- 1 Cost estimates based on R.S. Means Building Construction Cost Data.
- 2 Cost estimates based on previously supplied contractor costs.
- 3 Cost estimates based on quoted costs.
- 4 Total wall length is assumed to be 2300 feet long, 1 foot wide and 3 feet high.
- 5 The Knee Wall will be constructed in sections, and interconnected to ensure it is watertight.
- Annual O & M costs related to the knee wall are estimated at $10,000 per year.
- O&M shall include semi-annual inspections of knee wall to evaluate condition and continuity. The Village shall perform regular repairs as needed to maintain the knee wall.
Actual costs will be determined based on Phase II design specifications and contractor bid pricing.

## Total Project Costs
Item | Estimated Design/Construction Cost | Estimated Annual O&M Cost
Tide Valve Replacement | 287000 | 10000
Replace Drainage, Resurface Streets, New Curbs/Gutters (Assumes 25,000 ft of Roadway Improved) | 32925000 | 75000
Bulkhead Replacement | 1880000 | 10000
LIRR Knee Wall | 451000 | 10000
Permeable Parking Lots (2) | 570000 | 10000
Rain Gardens/Street Park Infiltration Beds (7) | 397000 | 21000
Bioswales (5) | 388000 | 15000
Bioretention Street Trees (50) | 1207000 | 20000
Beach Replenishment/Stabilization | 508000 | 10000
Total Proposed HMGP Drainage Improvements | 38613000 | 181000
HMGP Phase I Expenditures as of August 3, 2017 | 1376141.853
Estimated HMGP Project Total: | 39989141.853